## APPROVED 1 June 2017
GEN 7-2: Procurement Plan Sample
Procurement Plan for:
Project no and title: |  |  | 110023-19: Support to food security and livelihoods
Project timeframe: |  |  | 1 July 2017 - 31 Dec 2018
Donor: |  |  | DANIDA
Partner organisation: |  |  | Rural Farmers Association
Preparation date of plan: |  |  | 27 May 2018
Approval date of plan and by whom: |  |  |  | 1 June 2017 by GRN DCA HQ
Request(s) for derogation(s), if any: |  |  |  | None
The DCA Procurement Manual |  |  |  | 6 ed. 2016 |  | is applicable to the project
(Note: This template outlines the basic content of a procurement plan. Please add columns when of relevance to a given project.)
Procurement Plan for Supply, Service and Works
Budget line no. | Lot No. | Description of lots and items | Qty. | Note No. | Estimated cost incl. VAT and taxes EUR | Procurement procedure | Month needed at project site + start date |  |  |  |  | Actual Procurement
[7 empty] | A | B | C | D | E | Actual procurement procedure | Contractor selected | *Is the Contractor eligible? (Anti-terrorism etc.) | Actual Qty. | Contract value incl. VAT and taxes | Contract value incl. VAT and taxes | Voucher/ Transaction no.
[9 empty] | (A+B) |  | (D-C)
[7 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + costum clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
[16 empty] | (ILS) | EUR
(Note: remember to adjust activity plan)
[7 empty] | Days | Days | Days | Date | Date
SUPPLY
| Lot SUP 1 | Farming supplies
3.5.2 |  | Humic acid (can) | 6000 | 1 | 9000 |  | 10 | 7 | 17 | 2018-02-15 | 2018-01-20 |  |  |  | 600 | 37980.01 | 9000 | 1010045
3.5.1 |  | Traps | 300000 | 1 | 25200 |  | 10 | 20 | 30 | 2018-06-15 | 2018-05-15 |  |  |  | 300000 | 106344.02 | 25200 | 1010987
Total value Lot SUP 1 |  |  |  |  | 34200 | Negotiated | [5 empty] | Negotiated | H-Group | Yes |  | 144324.03 | 34200
| Lot SUP 2 | Hall rent
6.13 |  | Hall rent for farmers training | 10 |  | 2300 |  | 7 | 7 | 14 | 2018-02-15 | 2018-01-02 |  |  |  | 10 | 9706 | 2300 | 10700032
Total value Lot SUP 2 |  |  |  |  | 2300 | Simple | [5 empty] | Simple | Village Hall | Yes |  | 9706 | 2300
| Lot SUP 3 | Hygine Kits
2.1.5 | Lot SUP 3.1 | Toilet soap – 120 mg | 18585 pcs | 2 | 7793 |  | 22 | 5 | 27 | 2017-11-02 | 2017-10-05 | Negotiated | AH | Yes | 18585 pcs | 14229 | 12860 | 7697
2.1.1 |  | Laundry soap – 250 mg | 18585 pcs |  | 5694 | [9 empty] | 18585 pcs
2.1.3 | Lot SUP 3.2 | Soap bars - 140 mg | 5810 pcs |  | 2248 | [7 empty] | LTD international | Yes | 5810 pcs | 5023 | 4540 | 7699
2.1.2 |  | Laundry soap - 200 mg | 5810 pcs |  | 2248 | [9 empty] | 5810 pcs
2.1.4 |  | Liquid soap 110 ml | 1162 pcs |  | 329 | [9 empty] | 1162 pcs
Total value Lot SUP 2 |  |  |  |  | 18312 | Negotiated | [5 empty] | Negotiated |  |  |  | 19252 | 17400
SERVICE
| Lot SER 1 | Marketing Strategy
5.2.1 |  | Consultant on Marketing Strategy Development | 1 |  | 8000 |  | 7 | 7 | 14 | 01-12-2017 | 2017-11-15 |  |  |  | 1 | 42622.01 | 10100 | 10700032
Total value Lot SER 1 |  |  |  |  | 8000 | Simple | [5 empty] | Negotiated | Market Consult | Yes |  | 42622.01 | 10100
| Lot SER 2 | Book keeping
5.2.3 |  | Consultant on national book-keeping/taxation standards | 1 |  | 2400 |  | 7 | 7 | 14 | 01-10-2017 | 2017-09-15 |  |  |  | 1 | 11394 | 2700 | 1010802
Total value Lot SER 2 |  |  |  |  | 2400 | Simple | [5 empty] | Simple | Palestine Consult | Yes |  | 11394 | 2700
WORKS
| Lot WOR 1 | Construction
6.16 |  | Digging cisterns and plastering | 30 |  | 67500 |  | 20 | 15 | 35 | 2017-09-15 | 10-8-2017 |  |  |  | 27 | 256365.06 | 60750 | 1010254
Total value Lot WOR 1 |  |  |  |  | 67500 | Negotiated | [5 empty] | Negotiated | Ahmad group | Yes |  | 256365.06 | 60750
TOTAL PROCUREMENT PLAN VALUE |  |  |  |  | 46900 | [10 empty] | 483663.1 | 127450
Note 1: | Due to lack of warehousing capacity partial deliveries are needed
Note 2: | Partial deliveries. Second installment the 6th of October 2014
* Before issuing the order, please check the supplier's eligibility in the relevant databases as per donor request. Please indicate with a Yes, the the Contractor is eligible.

## 27 May 2017
ANNEX GEN 7-2: Sample Procurement Plan
Procurement Plan for:
Project no and title: |  |  | 110023-19: Support to food security and livelihoods
Project timeframe: |  |  | 1 July 2017 - 31 Dec 2018
Donor: |  |  | DANIDA
Partner organisation: |  |  | Rural Farmers Association
Preparation date of plan: |  |  | 27 May 2018
Approval date of plan and by whom: |  |  |  | <Insert>
Request(s) for derogation(s), if any: |  |  |  | None
The DCA Procurement Manual |  |  |  | 6 ed. 2016 |  | is applicable to the project
(Note: This template outlines the basic content of a procurement plan. Please add columns when of relevance to a given project.)
Procurement Plan for Supply, Service and Works
Budget line no. | Lot No. | Description of lots and items | Qty. | Note No. | Estimated cost incl. VAT and taxes EUR | Procurement procedure | Month needed at project site + start date |  |  |  |  | Actual Procurement
[7 empty] | A | B | C | D | E | Actual procurement procedure | Contractor selected | *Is the Contractor eligible? (Anti-terrorism etc.) | Actual Qty. | Contract value incl. VAT and taxes | Contract value incl. VAT and taxes | Voucher/ Transaction no.
[9 empty] | (A+B) |  | (D-C)
[7 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + costum clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
[16 empty] | ILS (Israeli Shekel Rate) | EUR (Euro)
(Note: remember to adjust activity plan)
[7 empty] | Days | Days | Days | Date | Date
SUPPLY
| Lot SUP 1 | Farming supplies
3.5.2 |  | Humic acid (can) | 6000 | 1 | 9000 |  | 10 | 7 | 17 | 2015-02-15 | 2015-01-20 |  |  |  | 600 | 37980.01 | 9000 | 1010045
3.5.1 |  | Traps | 300000 | 1 | 25200 |  | 10 | 20 | 30 | 2015-06-15 | 2015-05-15 |  |  |  | 300000 | 106344.02 | 25200 | 1010987
Total value Lot SUP 1 |  |  |  |  | 34200 | Negotiated | [5 empty] | Negotiated | H-Group | Yes |  | 144324.03 | 34200
| Lot SUP 2 | Hall rent
6.13 |  | Hall rent for farmers training | 10 |  | 2300 |  | 7 | 7 | 14 | 2015-02-15 | 2015-01-02 |  |  |  | 10 | 9706 | 2300 | 10700032
Total value Lot SUP 2 |  |  |  |  | 2300 | Simple | [5 empty] | Simple | Village Hall | Yes |  | 9706 | 2300
| Lot SUP 3 | Hygine Kits
2.1.5 | Lot SUP 3.1 | Toilet soap – 120 mg | 18585 pcs | 2 | 7793 |  | 22 | 5 | 27 | 2014-11-02 | 2014-10-05 | Negotiated | AH | Yes | 18585 pcs | 14229 | 12860 | 7697
2.1.1 |  | Laundry soap – 250 mg | 18585 pcs |  | 5694 | [9 empty] | 18585 pcs
2.1.3 | Lot SUP 3.2 | Soap bars - 140 mg | 5810 pcs |  | 2248 | [7 empty] | LTD international | Yes | 5810 pcs | 5023 | 4540 | 7699
2.1.2 |  | Laundry soap - 200 mg | 5810 pcs |  | 2248 | [9 empty] | 5810 pcs
2.1.4 |  | Liquid soap 110 ml | 1162 pcs |  | 329 | [9 empty] | 1162 pcs
Total value Lot SUP 2 |  |  |  |  | 18312 | Negotiated | [5 empty] | Negotiated |  |  |  | 19252 | 17400
SERVICE
| Lot SER 1 | Marketing Strategy
5.2.1 |  | Consultant on Marketing Strategy Development | 1 |  | 8000 |  | 7 | 7 | 14 | 01-12-2014 | 2014-11-15 |  |  |  | 1 | 42622.01 | 10100 | 10700032
Total value Lot SER 1 |  |  |  |  | 8000 | Simple | [5 empty] | Negotiated | Market Consult | Yes |  | 42622.01 | 10100
| Lot SER 2 | Book keeping
5.2.3 |  | Consultant on national book-keeping/taxation standards | 1 |  | 2400 |  | 7 | 7 | 14 | 01-10-2015 | 2015-09-15 |  |  |  | 1 | 11394 | 2700 | 1010802
Total value Lot SER 2 |  |  |  |  | 2400 | Simple | [5 empty] | Simple | Palestine Consult | Yes |  | 11394 | 2700
WORKS
| Lot WOR 1 | Construction
6.16 |  | Digging cisterns and plastering | 30 |  | 67500 |  | 20 | 15 | 35 | 2014-09-15 | 10-8-2014 |  |  |  | 27 | 256365.06 | 60750 | 1010254
Total value Lot WOR 1 |  |  |  |  | 67500 | Negotiated | [5 empty] | Negotiated | Ahmad group | Yes |  | 256365.06 | 60750
TOTAL PROCUREMENT PLAN VALUE |  |  |  |  | 46900 | [10 empty] | 483663.1 | 127450
Note 1: | Due to lack of warehousing capacity partial deliveries are needed
Note 2: | Partial deliveries. Second installment the 6th of October 2014
* Before issuing the order, please check the supplier's eligibility in the relevant databases as per donor request. Please indicate with a Yes, the the Contractor is eligible.