## Sheet1
ANNEX GEN 18-1: Sample of Procurement Documentation Template
(Sample is based on the DCA Procurement Manual 5ed, April 2016)
This template is a checklist to ensure proper filing of procurement documentation. It is a tool which enables the procurement responsible to monitor the procurement files and ensure proper documentation. Adjust the template as nessesary.
Project no.: 1803/1010028-03
Project title and period: Gender Rights and Access to Justice; 01/01-2013-31/12-20014
Added donor procurement guidelines: DCA Procurement Manual 4th ed 2012; EuropeAid Annex IV 2006
Name/Initals/Organization: Sanjib Gupta/SG/Freedom For All
Monitoring dates: 15/6-2013, 15/12-2013, 20/7-2014, 1/12-2014
Q&A during monitoring visits: Freedom for all inquired in to whether all documents must be saved in separate procurement files, or whether invoice could stay in finance unit. We recommended that complete procurement files are maintained and kept safely, however, the original invoice may stay with finance, whereas a copy shall be kep in the project procurement binder.
Derogations requested: For IT equipment (see General Procurement file)
General Procurement file | DCA Template/ documentation | Yes / No / Comment
Application/Grant Contract |  | yes
Procurement Plan with updates, budget | GEN 7-1 | yes, incl derogation
Donor communication (procurement related - e.g. derogations, VAT issues etc.) |  | yes
Signed Declaration of Impartiality and Confidentiality | GEN 2-1 | yes
Advertisement of Business Opportunities and responses received | GEN 8 | yes
Completed GEN 18. | GEN 18 | in process - to follow up on missing docs.
General Note to File |  | No
Lot Number and description as per Procurement Plan
|  | Lot SUP 1 Vehicles | Lot SUP 2 Booklets | Lot SUP 3 T-shirts | Lot SUP 1 Venue | Lot SUP 5 Stationary | Lot SUP 6 Hygine Kits | Lot SUP 7 Laptops | Lot SER 1 Legal Adv. | Lot SER 2 Consultant | Lot Ser 3 Cancelled | Lot WOR 1 Latrines | Lot X <title> | Lot X <title> | Lot X <title> | Lot X <title> | Lot X <title> | Lot X <title> | Add Columns
Place of procurement
Simple Procedure (Supply, Service, Works)
Copy of procurement request/RFQ/RFP (optional) | SUP 2; SUP 2-1; SER 1+2; WOR 1+2 |  | no | no |  | yes |  | yes | yes, TOR | yes, TOR
Proof of minimum 3 prices /quotations/proposals | SUP 1 / other documentation/ Note to File |  | yes, 3 | yes,3 |  | yes, 4 |  | yes | yes, 2 | yes
Evaluation/justification | Note to File / Evaluation Grid |  | yes | yes |  | yes, 4 |  | yes | yes | yes
Purchase Order/Contract | SUP 6; SER 4; WOR 4 |  | no, below EUR 2000 | yes |  | yes, 4 |  | yes | yes | yes
Copy of Invoice |  |  | yes | yes |  | no - to be located |  | yes | yes | yes
Shipping documents |  |  | NA | NA |  | NA |  | NA | NA | NA
Proof of receipt | SUP 13 / other doumentation |  | no - to be located | yes |  | yes |  | yes | yes | no - to be filed
Note to File |  |  | no | no |  | yes |  | no | no | no
COMMENTS | [7 empty] | Derogation in file |  |  | cancelled
Negotiated Procedure (Supply, Service, Works)
List of the suppliers/candidates | GEN 13 | yes, 6 shortlisted |  |  | yes, 5 shortlisted | [6 empty] | yes, 6 shortlisted
Copy of RFQ/RFP send to candidates | SUP 2; SUP 2-1; SER 1+2; WOR 1+2 | yes, 3 |  |  | yes | [6 empty] | yes
Received Quotations | SUP 2; SUP 2-1; SER 1+2; WOR 1+2 | yes, 3 |  |  | yes, 2 | [6 empty] | yes, 5
Evaluation Grid | SUP 4; SER 3; WOR 3 | yes |  |  | yes | [6 empty] | yes
Purchase Order/Contract | SUP 6; SER 2; WOR 1+2 | yes |  |  | yes | [6 empty] | yes
Letter to Unsuccessful Suppliers/Candidates | SUP 8; SER 5; WOR 5 | yes |  |  | yes | [6 empty] | yes
Copy of invoice |  | yes |  |  | yes | [6 empty] | no - find in finance file
Shipping documents |  | NA |  |  | NA | [6 empty] | yes
Proof of receipt | SUP 13 / other doumentation | yes |  |  | yes | [6 empty] | yes, completion report
Award Notice (optional for contracts below EUR 30,000) | GEN 17 | yes |  |  | NA | [6 empty] | NA
Note to File |  | yes |  |  | no | [6 empty] | yes
COMMENTS
Open Tender (Supply, Service, Works)
Tender Dossier | SUP 3; SER 6 | [5 empty] | yes
Tender Notice | GEN 11 | [5 empty] | yes
Tender Receipt Form | GEN 13 | [5 empty] | yes
Questions and Answers | GEN 14 | [5 empty] | no questions obtained
Tender Opening Minutes | GEN 15-1, GEN 15-2, GEN 15-3 | [5 empty] | yes
Tender Bids | SUP 3; SER 6 | [5 empty] | yes, 5
Evaluation Grid | SUP 5; SER 7 | [5 empty] | yes
Letter of Acceptance and Purchase Order/Contract | GEN 16; SUP 6; SER 4; WOR 2 | [5 empty] | yes
Letter to Unsuccessful Suppliers/Candidates | SUP 8; SER 5; WOR 5 | [5 empty] | yes
Copy of Invoice | [6 empty] | yes
Shipping documents | [6 empty] | NA
Proof of receipt | SUP 13 / other doumentation | [5 empty] | yes
Award Notice | GEN 17 | [5 empty] | no, due to security
Other documents (e.g. financial guarantees/govenement permissions) | [6 empty] | no
Note to File | [6 empty] | yes
COMMENTS | [6 empty] | security reasons are documented in file