## Sheet1
ANNEX GEN 7-2: Sample of Procurement Plan
Procurement Plan for:
Project no and title: ERP 110023-19: Support to food security and livelihoods
Project timeframe: 1-7-2014 till 31-12-2015
Donor: Danida funded
Partner org: Rural Farmers Association
Preparation date of plan: Prepared the 27 March 2014 - Updated 9 November 2015
Approval date of plan and by whom: 1st of April 2014 by Charlotte W. Sørensen
The DCA Procurement Manual 4th ed 1st revision 2013, is applicable for the project
Procurement Plan for Supply, Service and Works
Budget line no. | Lot No. | Description of lots and items | Qty. | Note No. | Estimated cost incl. VAT and taxes EUR | Procurement procedure | Month needed at project site + start date |  |  |  |  | Actual Procurement
[7 empty] | A | B | C | D | E | Actual procurement procedure | Contractor selected | Actual Qty. | Contract value incl. VAT and taxes | Contract value incl. VAT and taxes | Voucher/ Transaction no.
[9 empty] | (A+B) |  | (D-C)
[7 empty] | Time to carry out the procurement procedure (incl time for import/export permits and registration) | Delivery time by the supplier + transit time + costum clearance + local haulage | Total delivery time | Goods required by | Procure-ment start date
[15 empty] | ILS (Israeli Shekel Rate) | EUR (Euro)
(Note: remember to adjust activity plan)
[7 empty] | Days | Days | Days | Date | Date
SUPPLY
| Lot SUP 1 | Farming supplies
3.5.2 |  | Humic acid (can) | 6000 | 1 | 9000 |  | 10 | 7 | 17 | 2015-02-15 | 2015-01-20 |  |  | 600 | 37980.01 | 9000 | 1010045
3.5.1 |  | Traps | 300000 | 1 | 25200 |  | 10 | 20 | 30 | 2015-06-15 | 2015-05-15 |  |  | 300000 | 106344.02 | 25200 | 1010987
Total value Lot SUP 1 |  |  |  |  | 34200 | Negotiated | [5 empty] | Negotiated | H-Group |  | 144324.03 | 34200
| Lot SUP 2 | Hall rent
6.13 |  | Hall rent for farmers training | 10 |  | 2300 |  | 7 | 7 | 14 | 2015-02-15 | 2015-01-02 |  |  | 10 | 9706 | 2300 | 10700032
Total value Lot SUP 2 |  |  |  |  | 2300 | Simple | [5 empty] | Simple | Village Hall |  | 9706 | 2300
| Lot SUP 3 | Hygine Kits
2.1.5 | Lot SUP 3.1 | Toilet soap – 120 mg | 18585 pcs | 2 | 7793 |  | 22 | 5 | 27 | 2014-11-02 | 2014-10-05 | Negotiated | AH | 18585 pcs | 14229 | 12860 | 7697
2.1.1 |  | Laundry soap – 250 mg | 18585 pcs |  | 5694 | [8 empty] | 18585 pcs
2.1.3 | Lot SUP 3.2 | Soap bars - 140 mg | 5810 pcs |  | 2248 | [7 empty] | LTD international | 5810 pcs | 5023 | 4540 | 7699
2.1.2 |  | Laundry soap - 200 mg | 5810 pcs |  | 2248 | [8 empty] | 5810 pcs
2.1.4 |  | Liquid soap 110 ml | 1162 pcs |  | 329 | [8 empty] | 1162 pcs
Total value Lot SUP 2 |  |  |  |  | 18312 | Negotiated | [5 empty] | Negotaited |  |  | 19252 | 17400
SERVICE
| Lot SER 1 | Marketing Strategy
5.2.1 |  | Consultant on Marketing Strategy Development | 1 |  | 8000 |  | 7 | 7 | 14 | 01-12-2014 | 2014-11-15 |  |  | 1 | 42622.01 | 10100 | 10700032
Total value Lot SER 1 |  |  |  |  | 8000 | Simple | [5 empty] | Negotiated | Market Consult |  | 42622.01 | 10100
| Lot SER 2 | Book keeping
5.2.3 |  | Consultant on national book-keeping/taxation standards | 1 |  | 2400 |  | 7 | 7 | 14 | 01-10-2015 | 2015-09-15 |  |  | 1 | 11394 | 2700 | 1010802
Total value Lot SER 2 |  |  |  |  | 2400 | Simple | [5 empty] | Simple | Palestine Consult |  | 11394 | 2700
WORKS
| Lot WOR 1 | Construction
6.16 |  | Digging cisterns and plastering | 30 |  | 67500 |  | 20 | 15 | 35 | 2014-09-15 | 10-8-2014 |  |  | 27 | 256365.06 | 60750 | 1010254
Total value Lot WOR 1 |  |  |  |  | 67500 | Negotiated | [5 empty] | Negotiated | Ahmad group |  | 256365.06 | 60750
TOTAL PROCUREMENT PLAN VALUE |  |  |  |  | 46900 | [9 empty] | 483663.1 | 127450
Note 1: | Due to lack of warehousing capacity partial deliveries are needed
Note 2: | Partial deliveries. Second installment the 6th of October 2014