ANNEX GEN 9-1: Time Tables for Procurement Procedures

The following schedules are based on estimates of the time needed to carry out each Procurement Procedure.

| Time schedule for a Negotiated Procedure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 |
| Advertisement of Business Opportunities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare technical specifications/TOR and RFQ/RFP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RFQ/RFP bid flow. It is recommended that suppliers/candidates have at least 14-30 days to submit their quote |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of quotes’ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract negotiations and Award |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Delivery delay |  |  |  |  |  | Depending on commodity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Customs clearance |  |  |  |  |  | Depending on country |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Supplier’s delivery time to site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Time schedule for a Local Open Tender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 |
| Prepare technical specifications and tender documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advertisement of Tender Notice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender bid flow. It is recommended that suppliers/candidates have a minimum of 21 days to submit their Tender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender evaluation, clarifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract negotiations and Award |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract signing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Delivery delay |  |  |  |  |  |  |  |  |  |  | Depending on commodity |  |  |  |  |  |  |  |  |  |  |
| Customs clearance |  |  |  |  |  |  |  |  |  |  | Depending on country |  |  |  |  |  |  |  |  |  |  |
| Supplier’s delivery time to site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Time schedule for an International Open Tender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |
| Prepare technical specifications and tender documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advertisement of Tender Notice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender bid flow. It is recommended that suppliers/candidates have a minimum of 30 days to submit their Tender |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender evaluation, clarifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract negotiations and Award |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract signing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Delivery delay |  |  |  |  |  |  |  |  |  |  |  |  | Depending on commodity |  |  |  |  |  |  |  |  |  |
| Customs clearance |  |  |  |  |  |  |  |  |  |  |  |  | Depending on country |  |  |  |  |  |  |  |  |  |
| Supplier’s delivery time to site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |