ANNEX GEN 9-4: Sample of an Overall Work Plan

Overall Work Plan CHAM/DCA 2007 procurement activities

This work plan will be updated each month and sent to:

Elias M’bwana, CHAM (EM)

Nyirenda, CHAM

Desire, CHAM

Innocencia, DCA (IC)

Mercy, DCA (MK)

Malene, DCA (MRJ)

Project Officer (TBN in March)

| Action | Responsible | Done latest by | Done or pending |  |
| --- | --- | --- | --- | --- |
| - Contact ECHOs field office regarding visibility requirements for equipment | CHAM project officer and DCA, MK | 1/3 |  |  |
| - Publish general advertisement in the news paper | DCA, MK | 8/2 |  | done |
| - Submit request for derogation (lot 2, 3, 10, 7, 6a) | DCA, MK | 16/2 |  |  |
| - Follow up on point 2 | DCA, IC | 8/2 |  |  |
| - Check all market prices on materials (purpose is to reconfirm budget prices – and see if we are able to increase quantities on lot. 9. Community garden tools and lot 12.) | EM + IC | 19/2 |  |  |

| Lot no. | Description | Procurement procedure | Action | Responsible | Done latest by | Done or Pending |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 4wd vehicle | Negotiated | Draft specifications | DCA, MRJ | 9/2 |  |
|  |  |  | Make shortlist | CHAM, EM | 9/2 |  |
|  |  |  | Retrieve tax exemption letter | DCA, MK | 22/2 |  |
|  |  |  | Retrieve information from shipping agent on import documents | DCA MRJ/CHAM EM | 23/2 |  |
|  |  |  | Prepare and submit RFQ | DCA, MRJ | 16/2 |  |
|  |  |  | Evaluate quotes | DCA, CPH ProLog | 5/3 |  |
|  |  |  | Draft Purchase Order/Contract | DCA, MRJ | 8/3 |  |
|  |  |  | Send Letter to Unsuccessful Supplier | DCA, MRJ | 8/3 |  |
|  |  |  | Submit shipping documentation to obtain tax exemption | DCA, MRJ | TBA |  |
|  |  |  | Inspect and receive vehicle | CHAM, EM | TBA |  |
|  |  |  | Issue payment | DCA, MRJ | TBA |  |
| 2 | Motorcycles 12 units | Negotiated | Draft specifications | DCA, MRJ | 9/2 |  |
|  | Helmets 24 units |  | Make shortlist | CHAM, EM | 9/2 |  |
|  |  |  | Retrieve tax exemption letter | DCA, MK | 15/2 |  |
|  |  |  | Retrieve information from shipping agent on import documents | DCA, MRJ/CHAM, EM | 9/2 |  |
|  |  |  | Prepare and submit RFQ | DCA, MRJ | 16/2 |  |
|  |  |  | Evaluate quotes | DCA, CPH ProLog | 5/3 |  |
|  |  |  | Draft Purchase Order/Contract | DCA, MRJ | 8/3 |  |
|  |  |  | Send Letter to Unsuccessful Supplier | DCA, MRJ | 8/3 |  |
|  |  |  | Submit shipping documentation to obtain tax exemption | DCA, MRJ | TBA |  |
|  |  |  | Inspect and receive goods | CHAM, EM | TBA |  |
|  |  |  | Issue payment | DCA, MRJ | TBA |  |
| 3 | Bicycles | Simple | Draft specifications | DCA, IC | 28/2 |  |
|  |  |  | Collect quotations |  | 4/3 |  |
|  |  |  | Select supplier |  | 6/3 |  |
|  |  |  | Draft Purchase Order/Contract | DCA, MRJ | TBA |  |
|  |  |  | Inspect and receive goods | CHAM, EM | TBA |  |
|  |  |  | Issue payment | DCA, IC | TBA |  |
| 4 | Computer equipment | Simple | Draft specifications | CHAM, EM/DCA | 19/2 |  |
|  | 5 desktops |  | Collect quotations | DCA, IC | 19/2 |  |
|  | 1 laptop |  | Select supplier | DCA, Malawi committee | TBA |  |
|  |  |  | Draft Purchase Order/Contract | DCA, MRJ | TBA |  |
|  |  |  | Inspect and receive goods | CHAM, EM | TBA |  |
|  |  |  | Issue payment |  | TBA |  |
| 5 | Furniture | Simple | Draft specifications | CHAM, EM | 28/2 |  |
|  | - 3 Chairs |  | Collect quotations | CHAM, EM | 28/2 |  |
|  | - 3 Tables |  | Select supplier | CHAM, EM | 1/3 |  |
|  | - 3 Filling Cabinet |  | Draft Purchase Order/Contract | CHAM, EM | 1/3 |  |
|  |  |  | Inspect and receive goods | DCA, MRJ | 15/3 |  |
|  |  |  | Issue payment | CHAM, EM | 17/3 |  |
| 6A | Fruit tree seedlings | Negotiated | Draft specifications and distribution plan | CHAM, DM | 15/3 |  |
|  | - Orange |  | Make shortlist | DCA, MK /CHAM, EM | 15/3 |  |
|  | - Mango |  | Prepare and submit RFQ | CHAM, EM | 15/3 |  |
|  | - Papaya |  | Evaluate quotes | CHAM Committee | 15/4 |  |
|  | Delivered with PE tube |  | Draft Purchase Order/Contract | CHAM, EM | 15/4 |  |
|  | Training |  | Send Letter to Unsuccessful Supplier | DCA, MRJ | 20/4 |  |
|  |  |  | Inspect and receive goods | CHAM, EM | 1/5 |  |
|  |  |  | Issue payment | CHAM, EM | 5/5 |  |
| 9 | Community gardens | Negotiated | Draft specifications and distribution plan | CHAM, EM | 1/4 |  |
|  | - 390 hoes |  | Make shortlist |  | 2/4 | Done |
|  | -130 rake |  | Prepare and submit RFQ | CHAM, EM | 2/4 | Done |
|  | - 390 bush knives with |  | Evaluate quotes | DCA, MRJ | 18/4 | Done |
|  | Wooden handle |  | Draft Purchase Order/Contract | CHAM Committee | 18/4 |  |
|  | - 130 wheelbarrow |  | Send Letter to Unsuccessful Supplier | CHAM, EM | 22/4 |  |
|  | heavy duty |  | Inspect and receive goods | DCA, MRJ | TBA |  |
|  | - water cans 20L |  | Issue payment | CHAM, EM | TBA |  |
| 10 | Treadle pump | Negotiated | Draft specifications | CHAM, EM/DCA, MK | 1/4 |  |
|  |  |  | Make shortlist | DCA, MK/CHAM | 1/4 |  |
|  |  |  | Prepare and submit RFQ | CHAM, EM | TBA |  |
|  |  |  | Evaluate quotes | DCA, MRJ | TBA |  |
|  |  |  | Draft Purchase Order/Contract | CHAM Committee | TBA |  |
|  |  |  | Send Letter to Unsuccessful Supplier | CHAM, EM | TBA |  |
|  |  |  | Inspect and receive goods | DCA, MRJ | TBA |  |
|  |  |  | Issue payment | CHAM, EM | TBA |  |